## Instructions
NOTES AND INSTRUCTIONS: |  |  | ANNEX A
1. This template is part of the IC Circular relative to the PFRS 17 implementation.
2. Please use below instructions as guide in completing each tab.
3. The excel file must be saved using the following naming convention: <Company name acronym>_PFRS 17 Status Report_as of <dd/mm/2025>.
4. The excel file must be uploaded in the IC Online Uploading Portal on or before the submission due dates indicated in the IC Circular.
5. Once uploaded, the company must notify the Commission through an email following the format below:
| To: | hmodiv@insurance.gov.ph
| Subject: | <Company name acronym>_PFRS 17 Status Report_as of <dd/mm/2025>
A. PFRS 17 Status Report
Column | Header | Instructions For Completing - A. Status Report tab
Complete the Company Name and Period.
No deletion of activities is allowed but companies may add rows if there are activities performed not listed in the schedule.
A | Ref | A reference number used to list the activities taken as of the period.
B | Categories/Criteria | This column categorizes activities for PFRS 17 Preparedness/Implementation as follows: o Accounting Policies: Contract boundaries, level of aggregation, measurement models and risk adjustment, etc. o Data: Data to be used for measurement, transition approach, etc. o Systems: Related to IT, Accounting, Actuarial, etc. o Budget: Related to IT systems, trainings, etc. o Financial Impact: Related to Financial impact estimation of PFRS 17 o Others: Additional information/Others not scoped above
C | Activities | This column should be populated with specific activities in preparation for the PFRS 17 implementation on 1 January 2027. The list may not be comprehensive; companies can add rows for activities not included in the list.
D | Description, if applicable | This column should be populated with additional details of the activities. If the activity is not applicable, kindly put "N/A" and state the reason.
E | Responsible Department | This column should be populated with department responsible for each activity.
F | Planned Start Date | This column should be populated with dd/mm/yy by which the activity started.
G | Planned End Date | This column should be populated with dd/mm/yy by which the activity ended.
H | Current Status | This column should be populated with the current status. o Not Started o On Target o Delayed o At Risk o Completed
I | Remarks | This column can be populated should there be any additional information/remarks regarding the particular action/activity taken.
B. PFRS 17 Risk and Issues Tracking Log
Column | Header | Instructions For Completing - B. Risks and Issues Tracking Log tab
Complete the Company Name and Period.
For each issue identified, complete the following:
A | Issue ID | A unique ID number used to identify the issue in the issue tracking log.
B | Issue Description | This column should be populated with a description of the issue.
C | Date Created/Logged | This column should be populated with dd/mm/yy by which the issue is created/logged.
D | Issue Priority | This column should be populated with the priority of the issue as follows: o Critical: Issue will stop PFRS 17 Implementation progress if not resolved. o High: Issue will likely move the PFRS 17 Implementation progress back in terms of budget or timeline, or will materially affect quality or scope. o Medium: Issue will have material effect on PFRS 17 Implementation progress, has potential to be moved to high category and/or requires significant resources to manage. o Low: Issue is expected to have a moderate effect on the PFRS 17 Implementation progress, but will require resources to address.
E | Current Status | This column should be populated with the issue's current status. o Open: The issue is currently open but has not yet been addressed. o Work In Progress: The issue is being actively worked to develop a resolution. o Resolved: The issue is closed/resolved.
F | Impact Summary | This column should be populated with a description of the impact of the issue. The impact may be expressed in terms of one or more of the following: Accounting Policies, Data, Systems, Budget, Financial Impact, and Others.
G | Action Steps to Resolve/Address | This column should be populated with the proposed steps to address the issue.
H | Resolution Needed by | This column should be populated with dd/mm/yy by which the issue needs to be resolved.
I | Actual Resolution Date | This column should be populated with dd/mm/yy by which the issue was actually resolved.
C. PFRS 17 Preparedness
Column | Header | Instructions For Completing - C. PFRS 17 Preparedness tab
Complete the Company Name and Period.
A | Ref | A reference number used to list the Categories/Criteria.
B | Category/Criteria | This column categorizes activities for PFRS 17 Preparedness/Implementation.
C | Preparedness Level | This column should indicate the companies' preparedness based on A. Status Report: o Prepared: Complete/substantially complete; ready to implement PFRS 17 within three (3) months from the report date o Somewhat prepared: Partially complete; ready to implement PFRS 17 within twelve (12) months from the report date o Not prepared: Not yet started; not yet ready to implement PFRS 17 within twelve (12) months from the report date
D | Remarks | This column can be populated should there be any additional information/remarks regarding the particular PFRS 17 Preparedness category.
D. PFRS 17 Accounting Policies
Column | Header | Instructions For Completing - D. PFRS 17 Accounting Policies tab
Complete the Company Name and Period.
A | Areas | Provide company decisions on the following PFRS 17 areas: 1. Level of Aggregation 2. Estimate of Future Cash Flows 3. Discount Rates 4. Risk Adjustment 5. Contractual Service Margin 6. Embedded Guarantees 7. Financial Guarantee Contracts 8. Deferred Acquisition Costs 9. Premium Allocation Approach Measurement 10. Contracts with Direct Participation Features 11. Reinsurance 12. Transition

## A. Status Report
PFRS 17 STATUS REPORT | [7 empty] | ANNEX A
Company Name:
Period:
Ref | Categories/Criteria | Activities | Description, if applicable | Responsible Department | Planned Start Date | Planned End Date | Current Status | Remarks
1 | Accounting Policies | Drafting of accounting policies
2 | Accounting Policies | Revision of the accounting policies based on results of dry runs
3 | Accounting Policies | Finalization of accounting policies
4 | Accounting Policies | Approval of the accounting policies by the Board or senior management, whichever is applicable
5 | Accounting Policies | Chart of Accounts and Accounting Entries mapping
6 | Accounting Policies | Preparing Pro-Forma Financial Statement
7 | Accounting Policies | Chart of Accounts and Accounting Entries mapping – Dry Run
8 | Data | Data collection
9 | Data | Data workshop
10 | Data | Data validation and cleansing
11 | Data | Data transformation and tagging
12 | Financial Impact | Identification of unique contracts for contracts review and assessment
13 | Financial Impact | Contracts review and assessment
14 | Financial Impact | Identification of unique policies/products for financial impact assessment
15 | Financial Impact | Financial impact assessment and analysis
16 | Financial Impact | Preparation of Opening Balance Sheet (OBS)
17 | Financial Impact | Review of OBS and presentation to Board
18 | Financial Impact | Preparation of comparative figures
19 | Systems | Vendor evaluation and selection
20 | Systems | Confirmation of models and calculations
21 | Systems | System/s installation
22 | Systems | System/s and model configuration
23 | Systems | Details of the operating model (governance, processes, data, and IT) Note: Include other systems as applicable such as actuarial system, policy admin system, etc.
24 | Systems | Development and preparation of the Target Operating Model (TOM)
25 | Systems | System testing
26 | Systems | User acceptance testing (UAT)
27 | Systems | System handover from vendor
28 | Systems | System dry run
29 | Budget | Detailed plan definition, costs, and resources
30 | Budget | Approval of budget
31 | Budget | Revision and approval of revised budget, if applicable
32 | Others | Trainings
33 | Others | Communication to various stakeholders
34 | Others | Change management
35 | Others | Engagement with external auditors
Certified by:
(Signature over Printed Name of President/CEO/Equivalent Officer)
Note on A5: • Ref: A reference number used to list the activities taken as of the period
Note on B5: Category/Criteria: This column to categorize activities for PFRS 17 Preparedness/Implementation activities as follows: o Accounting Policies: Contract boundaries, level of aggregation, measurement models and risk adjustment, etc. o Data: Data to be used for measurement, transition approach, etc. o Systems: Related to IT, Accounting, Actuarial, etc. o Budget: Related to IT systems, trainings, etc. o Financial Impact: Related to Financial impact estimation of PFRS 17 o Others: Additional information/Others not scoped above
Note on C5: • Activities: This column should be populated with specific activities in preparation for the IFRS 17 implementation on 01 January 2026. The list may not be comprehensive, companies can add rows for activities not included in the list.
Note on D5: Description: This column should be populated with additional details of the activities. If the activity is not applicable, kindly put "N/A" and state the reason.
Note on E5: Responsible Department: This column should be populated with department responsible for each activity
Note on F5: Planned Start Date: This column should be populated with dd/mm/yy by which the activity started
Note on G5: Planned End Date: This column should be populated with dd/mm/yy by which the activity ended
Note on H5: • Current Status: This column should be populated with the current status. o Not Started o On Target o Delayed o At Risk o Completed
Note on I5: Comments: This column can be populated should there be any additional information/comment regarding the particular action/activity taken

## B.Risks and Issues Tracking Log
RISK/ISSUES MONITORING AND RESOLUTION LOG | [7 empty] | ANNEX A
Company Name:
Period:
Issue ID | Risk/Issue Description | Date Created/Logged | Issue Priority | Current Status | Impact Summary (if any) | Action Steps to Resolve/Address | Resolution Needed by | Actual Resolution Date
1
2
3
4
5
6
7
8
9
10
Certified by:
(Signature over Printed Name of President/CEO/Equivalent Officer)
Note on A5: • ID: A unique ID number used to identify the issue in the issue tracking log.
Note on B5: • Issue Description: This column should be populated with a description of the issue.
Note on C5: Date Created/Logged: This column should be populated with dd/mm/yy by which the issue is created/logged
Note on D5: • Priority: This column should be populated with the priority of the issue. Valid options include the following: Critical, High, Medium, Low. These are defined as follows: o Critical: Issue will stop PFRS 17 Implementation progress if not resolved. o High: Issue will likely move the PFRS 17 Implementation progress back in terms of budget or timeline, or will materially affect quality or scope. o Medium: Issue will have material effect on PFRS 17 Implementation progress, has potential to be moved to high category and/or requires significant resources to manage. o Low: Issue is expected to have a moderate effect on the PFRS 17 Implementation progress, but will require resources to address.
Note on E5: • Current Status: This column should be populated with the issue's current status. o Open: The issue is currently open but has not yet been addressed. o Work In Progress: The issue is being actively worked to develop a resolution. o Resolved: The issue is closed/resolved.
Note on F5: • Impact Summary: This column should be populated with a description of the impact of the issue. The impact may be expressed in terms of one or more of the following: Accounting Policies, Data, Systems, Budget, Financial Impact, Others
Note on G5: • Action Steps: This column should be populated with the proposed steps to address the issue.
Note on H5: • Resolution Needed by: This column should be populated with dd/mm/yy by which the issue need to be resolved
Note on I5: • Actual Resolution Date: This column should be populated with dd/mm/yy by which the issue was actually resolved

## C. PFRS 17 Preparedness
PFRS 17 PREPAREDNESS |  |  | ANNEX A
Company Name:
Period:
Ref | Categories/Criteria | Preparedness Level | Remarks
1 | Accounting Policies
2 | Data
3 | Financial Impact
4 | Budget
5 | Others
Overall
Certified by:
(Signature over Printed Name of President/CEO/Equivalent Officer)
Note on C5: o Prepared: Complete/substantially complete; ready to implement PFRS 17 within three (3) months from the report date o Somewhat prepared: Partially complete; ready to implement PFRS 17 within twelve (12) months from the report date Not yet started; not yet ready to implement PFRS 17 within twelve (12) months from the report date

## D. Accounting Policies
PFRS 17 ACCOUNTING POLICIES |  | ANNEX A
Company Name:
Period:
1. Level of Aggregation
2. Estimate of Future Cash Flows
3. Discount Rates
Discount Rate Approach:
4. Risk Adjustment
Risk Adjustment Approach:
Others (please specify)
5. Contractual Service Margin
6. Embedded Guarantees
7. Financial Guarantee Contracts
8. Deferred Acquisition Costs
9. Premium Allocation Approach Measurement
10. Contracts with Direct Participation Features
11. Reinsurance
12. Transition
Transition Approach:
Others (please specify)
Certified by:
(Signature over Printed Name of President/CEO/Equivalent Officer)
Bottom-up
Top-down
Combination
Cost of Capital
Value at Risk
Margin for Adverse Deviation
Others
Full retrospective approach
Modified retrospective approach
Fair value approach
Combination
`